# NullScale Project Update: Is It the Length or the Look-Alikes?

Progress Report — October 4, 2026 · M. I. Mahmud and Jayden, under Prof. Justin Zhan · Target: NAACL 2027

# 1. The project in one paragraph

When a language model is asked a question whose answer is not in a long document, it should say “not found”. Instead it often makes up an answer. Roig (2026) showed this gets worse as documents get longer — but longer documents also hold more records that look like the thing being asked. So nobody knows which one is the cause: the length, or the look-alikes. Our idea: to answer, a model needs only one matching record; to refuse, it must reject every record. So one convincing look-alike may be enough to cause a made-up answer, whatever the length. We build every document ourselves so we control both, and we prove the answer is absent. We test four research questions (RQ1–RQ4) across seven open models.

# 2. Progress so far

- Steps 1 to 7 of the 11-step plan are complete, plus the full Exp 1, Exp 6 and Exp 7 analysis.

- Generator (NullScale) built and verified: fake business world → look-alike ladder (4 levels, 2 kinds) → filler → exact-length documents → 12 questions each → a checker that proves every no-answer question is truly unanswerable.

- Dataset built: 565 documents, 6,780 questions per model; every document within 0.1% of target length; all absence checks pass.

- Scoring rules (fixed rules, no AI judge): 47/47 unit tests pass; agree with RIKER2’s own scorer on 99.2% of 605,948 answers.

- All 7 models run on the H200 cluster for Exp 2, Exp 3 and Exp 4, plus the three temperature-0.7 repeats of Exp 2.

- Exp 1 (Roig’s RIKER2 re-analysis), Exp 6 (real Wikipedia text) and Exp 7 (12-in-one-call) all run and scored; ~145,000 answers scored this round.

- Still to do: Exp 5 fixes, the 300-answer hand audit, and the final paper figures.

# 3. Models applied (all 7 open models + re-analysis)

- Qwen3 4B, Llama 3.1 8B — small, also run on the PC for testing.

- Gemma 3 27B, Qwen3 30B-A3B — mid-size.

- Llama 3.3 70B (FP8), Qwen3-Next 80B (FP8), GLM-4.5-Air (FP8) — large.

- Exp 1 re-uses Roig’s released answers from 35 models (RIKER2); 11 have answers at all three lengths.

- Hardware: 8× H200 (141 GB) on the UC ARCC2 cluster; data-parallel, several models at once.

# 4. Results so far

## RQ1 — Do stronger look-alikes cause more made-up answers? (Exp 2, 32K fixed length)

- Every model is near 0% with no look-alike and 65–94% with one strong look-alike.

- Most made-up answers copy the look-alike’s exact value (94–99% for 6 of 7 models; Gemma 58%).

- Numbers are stable across three temperature-0.7 repeats (within ~3 points).

Table 1. Made-up answer rate (%) by look-alike level, 32K, T=0 [95% interval].

| Model | none | weak | medium | strong | copied look-alike |
| --- | --- | --- | --- | --- | --- |
| Qwen3 4B | 0.0 | 0.4 | 15.8 | 65.0 | 99% |
| Llama 3.1 8B | 0.4 | 0.8 | 14.6 | 64.6 | 98% |
| Gemma 3 27B | 5.0 | 22.1 | 71.2 | 90.8 | 58% |
| Qwen3 30B-A3B | 1.7 | 9.6 | 25.8 | 82.9 | 96% |
| Llama 3.3 70B | 0.0 | 5.4 | 44.2 | 94.2 | 95% |
| Qwen3-Next 80B | 0.0 | 0.0 | 24.6 | 86.7 | 98% |
| GLM-4.5-Air | 0.4 | 10.4 | 24.2 | 93.3 | 94% |

Figure 1 (Exp 2). Made-up answers rise sharply with look-alike strength at a fixed 32K length, on both the name ladder (a) and the role ladder (b).

## RQ2 — Does length alone cause more made-up answers? (Exp 3)

- With a strong look-alike present, the made-up rate is high and flat from 8K to 128K for every model.

- With no look-alike, the rate stays near 0% for most models at every length.

- Exchange rate: one strong look-alike ≈ 6–8 doublings of length (a document ~60–250× longer). Both terms matter in the regression, but the look-alike effect is far larger (odds ratio ~120 vs. ~1.1 per doubling).

- Two exceptions (a genuine finding): Llama 3.3 70B at 128K jumps to 74% even with no look-alike, and Gemma 3 27B rises at 64K. In both, accuracy on answerable questions also drops — this is a reading breakdown at long length, not a look-alike effect.

Figure 2 (Exp 3). (a) With no look-alike, length alone barely moves the rate for most models (the two exceptions are reading breakdowns). (b) With a strong look-alike, the rate is high at every length.

## RQ1 (dose) — More copies of the same look-alike (Exp 4)

- Made-up answers rise from 1 to 2–4 copies, then fall at 8 copies for most models (the repeated record starts to look like a list, not a single fact).

Figure 3 (Exp 4). Effect of 1, 2, 4, 8 copies of the same strong look-alike at 32K.

## RQ4 (early sign) — Sibling padding helps (Exp 3, filler type)

- Replacing unrelated filler with sibling filler (same-kind records that clearly lack the fact) lowers made-up answers in every model (by 2–20 points).

Figure 4. Sibling filler reduces made-up answers vs. unrelated filler (strong look-alike, all lengths).

## RQ3 — Does Roig’s released data show the same pattern? (Exp 1, RIKER2)

- Our reading matches Roig’s published rates exactly (0.00-point difference, 465 settings) — a correctness check.

- Look-alikes do NOT grow with length in RIKER2 (~62% of trap questions have one at every length).

- At fixed 32K, same question type: look-alike present 42.5% vs. none 19.1% made up — look-alikes matter here too.

- But RIKER2 also shows a length effect with no look-alike — a useful tension (its long documents pack far more same-kind records our strict definition does not count).

Figure 5 (Exp 1). Roig’s released answers, split by look-alike presence, at 32K/128K/200K. Left: all trap questions; right: same question type only.

## Real-text check and protocol check (Exp 6, Exp 7)

- Exp 6 (real Wikipedia, answer passage removed) backs the main claim: with random surrounding passages, models almost never make up an answer (0–4%); with look-alike passages, they make up answers 48–87% of the time, at both 8K and 32K.

- Exp 7 (12 questions in one call) makes the problem worse: Qwen3 4B 63% → 76%; Llama 3.1 8B 58% → 95% — supports asking one question per call.

Figure 6 (Exp 6). Real Wikipedia text: look-alike passages cause made-up answers; random passages almost never do.

# 5. Does it support our proposal claims?

- RQ1 — YES. Stronger look-alikes clearly cause more made-up answers at fixed length, in every model; most answers copy the look-alike’s value.

- RQ2 — YES. With look-alikes fixed, length alone barely moves the rate; the exchange rate (≈6–8 doublings) is high. Two long-length reading breakdowns are reported honestly as separate failures.

- RQ3 — MIXED / USEFUL. Our controlled experiments say look-alikes dominate; Roig’s data shows look-alikes matter at fixed length but also a length effect we can explain. This tension strengthens the paper rather than weakening it.

- RQ4 — EARLY YES. Sibling padding already lowers made-up answers; the full fix comparison (Exp 5) is the next step.

- Overall message (so far): Control what goes into the context, not only how much. One convincing look-alike is worth dozens of doublings of length.

# 6. Next steps

- Write and run Exp 5 (sibling padding vs. strict prompt, reranker, fact-checker, at equal cost).

- 300-answer hand audit (both authors label independently; measure agreement).

- Re-check the Exp 6 control scoring (strict exact-match may undercount correct answers), and optionally rerun Llama 3.3 70B at 128K in full precision.

- Build the final paper figures and tables.